Quiz – Scheduling						Name: _________________

David Lippman – W10

Show appropriate work

| Task | Time required | Tasks that must be completed first |
| --- | --- | --- |
| A | 3 |  |
| B | 4 |  |
| C | 7 |  |
| D | 6 | A |
| E | 5 | A |
| F | 5 | B |
| G | 4 | D, E |

- a. Create a digraph for the set of tasks above

b. Schedule these tasks on three processors using the priority list: A, B, C, F, E, D, G.

c. What is the optimal finishing time (a.k.a. minimum completion time / critical time) for this set of tasks?

- Using the digraph below,

T9 (5)

T1 (6)

T5 (4)

T2 (2)

T8 (3)

T6 (7)

T10 (6)

T3 (10)

T11 (8)

T7 (5)

T4 (4)

a. Create a priority list for the digraph above using the Decreasing Time Algorithm.  Then schedule the tasks on two processors.

Priority List: ___________________________________________________________

b. Create a priority list for the digraph above using the Critical Path Algorithm.  Then schedule the tasks on two processors.

Priority List: ___________________________________________________________